Chase Hanes

LIS 688

14 April 2016

Grant Assignment

‘Dear Diary, Let Words Tell My History Best: African American Confederate Civil War Diaries’

I chose this title for the project to highlight the importance of the regiment’s diaries in being the storytellers and truth givers of the regiment’s history. I want their words to be commemorated and valued.

- As I looked for various grant options, I searched broadly at a national level by looking at NHPRC Grants. I then narrowed my search to the state level by browsing North Carolina’s site for LSTA funds. Applying for a grant at the state level heightens the chances for receipt of award, but I had to stop and reconsider the overall significance of the project. The‘Dear Diary, Let Words Tell My History Best: African American Confederate Civil War Diaries’ project (hereafter referred to as the Let Words Tell My History Best project) has relevancy on a scale far outside North Carolina heritage and memory. The diaries of the African American Confederate Regiment offer insight into Southern regional history, but at an even more significant level, they are primary documents of irrefutable value to national history. The writers of these diaries offer a perspective of black people as agential, with all the nuanced emotions and thoughts indicative of human life, despite the injustice and discrimination plaguing them. Their stories are critical in understanding local history, North Carolina history, southern history, but also the history of America. Thus, I chose to look at the national level again and apply for a grant from the National Endowment for the Humanities.

The ‘Humanities Collections and Reference Resources Grant,” which is part of NEH’s Division of Preservation and Access, could benefit the Let Words Tell My History Best project very well. A link to the grant can be found here: http://www.neh.gov/grants/preservation/humanities-collections-and-reference-resources

There are two facets of this award: implementation and planning/assessment. Both facets of the grant would be critical. An important part of this grant is that it focuses on preservation and digitization. Many grants I searched serve just preservation or just digitization projects. However, this grant description states, “Funding from this program strengthens efforts to extend the life of…materials and make their intellectual content widely accessible, often through the use of digital technology.” Because the diaries are in such poor condition and also need digitization, preservation and digitization need to occur. Privileging one over the other should be considered in only dire circumstances. Digitizing can exacerbate the already fragile condition of the diaries, and preservation alone can limit access to users unable to visit the Heritage Center. Thus, a project that balances these two components is necessary.

Beyond looking at grant requirements and guidelines, I also was able to see previous projects that this specific grant funded. Projects in previous years were actually quite similar to my projected scope for Let Words Tell My History Best. The Free People of Color in Louisiana: Revealing an Unknown Past project by Louisiana State University received funding from this grant in 2012. In terms of number of materials digitized and emphasis on preservation, the projects are similar. Moreover, both projects have an aim to tell stories primarily glossed over by systemic racism.

I do realize that the grant is awarded for the period of one year, but as I was planning out the project, I extended services to two years. Previous recipients of this grant wrote narratives that extend the projects to 2+ years, so I followed in that fashion.

- Audience and Need:

The constituencies to whom Let Words Tell My History Best serve are very vast. At a local level, members of our town (Noplace, NC), K-12 teachers, students, life-long learners, and amateur historians will utilize our online project and/or frequent the Heritage Center to access the preserved, on-site materials. However, the appeal does not simply relegate this project to regional heritage; patrons interested in Southern History, Civil War History, or Nineteenth Century African American History will learn much from this content. Because of the descriptions of medical treatment on the battlefield in the diaries and their rich evaluation of the emancipation of Black, southern slaves, we anticipate scholars of medical history and post-bellum/ Reconstruction economics will be highly interested in these primary source documents.

We also anticipate a large number of users coming from our various partner institutions. There are several partner institutions involved in Let Words Tell My History Best and we will offer more detailed information about various partners in subsequent sections. However, students and faculty members affiliated with our partners will be prime users of the digitization project and on-site materials. The small, liberal arts women’s college Mount Holypine has several departments contributing to the project. Women’s and Gender Studies, African American Studies, History, and African American Diaspora are departments involved in the project. The diaries of regiment member Elliot George are of particular interest to the Women’s and Gender Studies Department because George (known as Emily George) was actually amongst the number of over 400 women who concealed their identities and fought alongside men in the Civil War. Thus, a large facet of the outreach from the production team will focus on Emily George’s subversion of racial and gender stereotypes of her time—with the motive of sparking interest from Women’s and Gender Studies students. The descriptions of female lives contained in all of the diaries, regardless of their male authorship, are intellectually significant to these particular students.

The archives at two large universities in the neighboring counties will also be partners in the project. They have proclaimed that their English Departments and African American Studies Departments are very interested, so we anticipate students and faculty from those disciplines using our materials. Classes in the English Departments at both universities that teach life writing are interested in studying the various diaries. Three different African American churches in the county are also partnering with us and we anticipate members from their congregations (some of whom are descendants of the diarists) utilizing the documents.

While we expect a large portion of our constituencies to be students and faculty at our partner institutions, we anticipate that the majority of our patrons will be independent scholars of the Civil War, American History, Women’s and Gender Studies, and, primarily, African American History.

Through weekly discussions with our institutional partners in the last three months, our team initially identified basic preservation needs for this project such as rehousing fragile diaries in archival boxes, locating sufficient storage space within the Heritage Center, purchasing protective sleeves for specific pages, and extensively preserving/rebinding 100 of the 250 diaries with the most important archival value. The remaining 150 diaries will be preserved in the best way possible, but priority is given to those 100 diaries that are legible, cohesive (without missing fragments), and have no signs of mold or dry rot. The 150 diaries that are exceedingly acidic, that have mold spots, or that have a significant number of missing sections will be preserved in the most appropriate fashion (once mold is isolated and contained), but primary concern for these documents will be given to digitization. Because the majority of the diaries are in such poor condition with missing covers or loose bindings, digitization actions are critical. We hope to digitize all pages of the diaries—even those pages from the 100 volumes that are in relatively good condition.

In a survey given to community members of Noplace, NC, students and faculty at partner institutions, and congregation members at partner churches, we have identified four diarists whose work has incited the highest attention. These 40 volumes (5,426 pages) will be transcribed in full. We anticipate transcribers will work on this for the first year. The remaining diaries that focus specifically on the Civil War will be transcribed at a minimal level: transcribers (most likely students doing coursework) will take note of specific data points such as the date of the entry, the casualties listed, any names or people with whom the diarist interacted, or place names. Tags will then be created on the website interface to connect users to specific entries. (The transcription at this level will be done towards the later period of the project.)

In discussions with the project team across various institutions, we firmly believe that benefactors of this project need increased access, especially in virtual forms, to the diaries. A single online service point would allow for users to understand the lives depicted in Let Words Tell My History Best from multiple perspectives and academic disciplines. The single interface would allow diverse patrons to access the digitized materials regardless of their academic expertise or affiliation with certain repositories. Expanded and augmented access to these diaries via virtual digitization allows for stories—stories hushed and silenced by history—to reach a broadened demographic.

- Project Description Narrative

The antebellum African American body is seen as tortured, in a perpetual state of victimhood. While slavery unjustly dehumanized and ravaged the majority of the African American population, these individuals were still able to be creative and innovative in the face of so much oppression. Their choices were inhibited by racism, but their lives were still meaningful. Dear Diary, Let Words Tell My History Best: African American Confederate Civil War Diaries is a project that tells the courage and humanity of African American individuals that fought for the Confederacy in the Civil War. The project will preserve and digitize the 250 diaries of an African American Confederate Regiment that fought at the Battle of Gettysburg and other prominent battles in the south. Their story disrupts the narrative that places Nineteenth Century African Americans as merely victims—nothing more. The stories of the regiment reveal that African Americans could be powerful and pursue their own formation of identities. They were cruelly and inhumanely oppressed, but they were so much more than just slaves or subjugated victims of racism; they were creators of American History.

Let Words Tell My History Best is a two year project that will digitize the contents of the diaries covering dates between 1860 and 1870 and allow for free access to them online. Project staff will digitize 34,720 pages (approximately 70 pages for each digitizer per day) to increase access to students, researchers, and the general public. The project entails the development of more in-depth virtual finding aids as well as preservation of the volumes that are increasingly becoming unbound or are missing covers. Preservation and conservation of these items will ensure that the diaries will eventually be available for free public access.

The website that we will create (starting January 2018) will serve as the virtual repository database for the digitized diaries. It will augment access but also unite other collections at partnering institutions across North Carolina. Each online finding aid for the diaries will link out to collections/papers of descendants or related materials housed at various repositories. For example, the woman who taught three of diarists how to write has her own collection of drawings and diaries at Mount Holypine College, a partner institution. Our collection websites and finding aids will link to one another. Through this convergence of collections and repositories, users will gain a more complex sense of North Carolina history.

Of augmented importance in this project is the diaries’ intellectual significance to Women’s and Gender Studies scholarship. The diaries of regiment member Elliot George are of particular interest because George (known as Emily George) was actually amongst the number of over 400 women who concealed their identities and fought alongside men in the Civil War. As a free African American woman, she joined her enslaved husband to fight for the Confederacy. Thus, a large facet of the outreach from the production team will focus on Emily George’s subversion of racial and gender stereotypes of her time. The diaries also contain rich descriptions of female lives as various women enter into the daily proceedings of the diarists.

3.a) Partners: Partners were selected due to their commitment to archival research, archival preservation, and digitization expertise. Each partner has a unique perspective in interpreting the diaries and can offer supplemental materials (such as related collections or ancestral testimonies) that can provide further context for the diarists words.

- The Noplace Cultural Heritage Center is the lead institution for the project. The center will be the epicenter in which the Project Manager is based, where the digitization, re-binding, and preservation takes place, and where metadata is created. The Noplace Cultural Heritage Center will also be in charge of website hosting and long-term storage.

- Mount Holypine College: This small, liberal arts women’s college has several departments contributing to the project. Women’s and Gender Studies, African American Studies, History, and African American Diaspora are departments involved. Many faculty and students from the Women’s and Gender Studies Department have expressed interest in the Emily/Elliot George (woman soldier) diaries. We anticipate that modern feminist approaches can be a lens for interpreting these diaries. Several professors have structured potential classes around the diaries, so we anticipate that some of the transcription work for the project can come from students’ class assignments. Much of the digitization work will come from student interns at this college.

- Blair University, a historically Black college in a neighboring county, has archival material in its small archive. Part of its mission is to further the distribution of African American History from slavery to modern times. It will provide supplemental context to the diaries, metadata, and outreach support. The Library and Information Studies Department has expressed interest in allowing students to do archival practicums with the project.

- Sinclair University, a large university in a neighboring county, has been an institutional partner with the Noplace Heritage Center many times before. We recently completed a digitization project concerning early 20th Century Vogue Magazines (the digitization occurred at a Montclair University with proper equipment; because Let Words Tell My History Best does not fall under the scope of Montclair’s archival mission, they are not involved in the project). Sinclair’s students from the Composition and Rhetoric Department and Mass Media/Communications Department did internships on that previous project. For this current project, faculty and students in Life Writing Classes have offered to help do transcription work.

- Tabernacle United Methodist Church: This historically Black church was founded by one of the diarists. He was instrumental in funding the church organ. The church has supplemental documents relating to his life.

- Noplace Baptist Church has several members that are descendants of the diarists. Supplemental materials in the church archive would be very helpful for genealogists.

- Lighthouse Church of God is another historically Black church with a very extensive archive. The church started as an outdoor meeting place for newly emancipated slaves to worship, so many of the oldest documents in the archive concern life in the south during the Reconstruction era.

- Project Activities

- We anticipate that 14 diary pages can be scanned per hour.

- This translates to 70 diary pages per day if a digitizer works 5 hours per day.

- If a digitizer works 4 days per week (culminating in a 20 hour work week), 280 pages can be digitized per day.

- We anticipate having two interns each semester from Mount Holypine College digitizing materials. This culminates to 560 diary pages digitized per week.

  - Summer 2017 (6 weeks of digitizing): 3,480 diary pages

  - Autumn 2017 (14 weeks of digitizing): 8,120 diary pages

  - Spring 2018 (15 weeks of digitizing): 8,400 diary pages

  - Summer 2018 (8 weeks of digitizing): 4,480 diary pages

  - Autumn 2018 (14 weeks of digitizing): 8,120 diary pages

  - Spring 2019 (4 weeks of digitizing): remaining 2,120 diary pages

Two transcribers will work for the first 20 weeks of the project transcribing the 40 diaries identified for full transcription. One diary (of pages varying from 100 – 200 in length) will be transcribed per week. Both transcribers will have roughly the same number of pages to transcribe.

Year One: May 2017 – April 2018

| Projected Date | Activity | Primary Responsibility |
| --- | --- | --- |
| May 2017 | Advertise for two graduate student assistant positions (from Mount Holypine College) that will begin in June of 2017 | Noplace Cultural Heritage Center (two volunteer staff) and Mount Holypine College |
|  | Advertise for two transcribers (who will fully transcribe the identified 40 volumes) to start in June of 2017 | Project Manager and Sinclair University |
|  | Upon accrual of funds, Noplace Cultural Heritage Center will purchase and install work stations and an Fujitsu Scansnap Sv600 Contactless Scanner | Project Manager from Noplace Cultural Heritage Center |
|  | Retrieval of an Epson Expression 10000xl Scanner on loan from Sinclair University | Project Manager from Noplace Cultural Heritage Center (loaned from Sinclair University) |
|  | Hiring of preservationist/conservationist to rebind and properly preserve prioritized diaries | Blair University |
|  | Outreach projects to notify the community of the project | Noplace Cultural Heritage Center (two volunteer staff), Tabernacle United Methodist Church, Noplace Baptist Church, Lighthouse Church of God |
|  | Purchasing of 25 archival boxes (10 diaries per box) | Noplace Cultural Heritage Center (volunteer staff) |
|  | Purchasing of new storage cabinet away from any windows or threat from a leaking HVAC system | Project Manager |
|  | Purchasing of three hard-drives for metadata and scanning information | Noplace Cultural Heritage Center (volunteer staff) |
|  | Purchasing of small protective encasements for each diary | Project Manager (assisted by preservationist’s suggestion) |
| June 2017 | Preservationist starts working with materials in need of repair | Preservationist |
|  | Preservationist and Project Manager develop a prioritized plan for digitization | Project Manager and Preservationist |
|  | Review of the plan for prioritized digitization with student Interns from Mount Holypine College; | Project Manager, representatives from partner institutions, Mount Holypine College Interns |
|  | Sparse elaboration on the collection level finding aids (the years of specific volumes, the scope of the diary; not diary entry-level or extensively processed) | Project Manager, Mount Holypine College Interns, Noplace Cultural Heritage Center Volunteers |
|  | Student Interns from Mount Holypine College are trained and start digitizing the materials that are in the best shape | Project Manager, representative from Sinclair University, Mount Holypine College Interns |
|  | Quality Control of Student Work | Project Manager |
|  | Two transcribers begin transcribing the 40 volumes (estimated one volume for each transcriber per week) | Transcribers |
|  | Partner Meeting | Mount Holypine Representative (leads), partner representatives and Project Manager attend |
| August - September 2017 | Preservationist continues working with materials in need of repair | Preservationist |
|  | Continued elaboration on finding aids (continues throughout project) | Project Manager, Mount Holypine College Interns |
|  | Student Interns from Mount Holypine College continue to digitize materials (continues throughout project) | Mount Holypine College Interns |
|  | Transcribers continue to transcribe | Transcribers |
|  | Partner Meeting (one every two months) | Mount Holypine Representative (leads), Partners |
| October – November 2017 | Advertisement for Spring 2018 graduate student assistants (for digitization) | Noplace Cultural Center volunteers and Mount Holypine College |
|  | Advertisement for Spring 2018 graduate student assistants (for online interface construction) | Noplace Cultural Center volunteers, Blair College |
|  | Advertisement for website/database developer that can train student interns and project manager | Noplace Cultural Center volunteers, Blair College |
| December 2017 | Preservationist finishes | Preservationist |
|  | Interns for Spring 2018 are hired | Project Manager |
|  | Website/ Database trainer is hired | Project Manager |
|  | The 20 weeks of the digitization (from mid-June to early December) produces 11,200 digitized pages | Mount Holypine College Interns |
|  | Purchasing of three new computers (for website developers) | Project Manager |
|  | Transcribers finish transcribing the 40 diaries identified for FULL transcription | Transcribers |
| January 2018 | Training of 2 Mount Holypine graduate student assistants | Project Manager |
|  | Training of 2 Blair College website design assistants | Website/ Database trainer |
|  | Outreach projects to notify public of the project’s progress | Noplace Cultural Heritage Center (two volunteer staff), Tabernacle United Methodist Church, Noplace Baptist Church, Lighthouse Church of God |
|  | Training of graduate student assistants with finding aid creation | Website/ Database Trainer |
|  | Quality Control of Student Work | Website/ Database Trainer, Project Manager |
|  | Metadata compiled | Blair University interns |
|  | Partner Meeting (one every two months) | Mount Holypine Representative (leads), Partners |
| February 2018 | A plan prioritizing which digitized diaries appear online first is developed | Project Manager, Mount Holypine College Interns, Blair University Interns, representatives from partner institutions |
|  | Assessment of digitization progress | Project Manager |
| February-March 2018 | Digitized diary pages start appearing on the online database | Blair University interns |
|  | Finding aids start appearing on the online database | Blair University interns |
|  | Digitization continues | Mount Holypine College interns |
|  | Metadata compiled | Blair University interns |
|  | Partner Meeting (one every two months) | Mount Holypine Representative (leads), Partners |
| April 2018 | Advertisements for Summer 2018 Mount Holypine College Interns (2 for digitization) and Advertisements for Fall 2018 internships (if summer interns decide not to continue with the project in the fall) | Noplace Cultural Heritage Center (2 volunteers), Mount Holypine College |
|  | Advertisements for 2 Summer 2018 website interns from Blair University and Advertisements for Fall 2018 internships (if summer interns decide not to continue with the project in the fall) | Noplace Cultural Heritage Center (2 volunteers), Blair University |
|  | Website developer/ trainer finishes duties | Website developer/ trainer |
|  | The total number of digitized pages produced is now 20, 000 | Mount Holypine College interns |
|  | End of year project assessment | Project Manager, representatives from partner institutions |
| END of Year 1 |  |  |

Year Two: May 2018 – April 2019

| Projected Date | Activity | Primary Responsibility |
| --- | --- | --- |
| May 2018 | Student workers for digitization are hired | Project Manager and Mount Holypine College |
|  | Student workers for continued website/ database development are hired | Project Manager and Blair University |
|  | Outreach projects to notify the community of the progress/ continued goals of the project | Noplace Cultural Heritage Center (two volunteer staff), Tabernacle United Methodist Church, Noplace Baptist Church, Lighthouse Church of God |
|  | Purchasing of three new hard-drives for metadata and scanning information | Noplace Cultural Heritage Center (volunteer staff) |
|  | Review of prioritized summer digitization plan/ training of student interns from Mount Holypine in digitization | Project Manager |
|  | Elaboration on finding aids | Blair University Interns, Mount Holypine College Interns |
|  | Quality Control of Student Work | Project Manager |
|  | Partner Meeting | Mount Holypine Representative (leads), partner representatives attend |
| June - July 2018 | Digitization continues | Mount Holypine College Interns |
|  | Digitized diary pages are continually placed online accompanied by finding aids | Blair University Interns |
| July 2018 | Volunteer Preservationist quickly assesses the condition of materials | Volunteer Preservationist |
|  | End of summer season; the total number of digitized pages is now 24,480 | Mount Holypine College Interns |
|  | Website displaying what has been digitized so far will launch | Blair University Interns |
|  | End of the summer partner meeting | Mount Holypine Representative (leads), partner representatives attend |
| August - September 2018 | Student workers for digitization (if not the same interns from the summer of 2018) are hired and trained | Project Manager |
|  | Student workers for continued website/ database development (if not the same interns from the summer of 2018) are hired | Project Manager |
|  | Outreach projects to notify the community of the progress/ continued goals of the project | Noplace Cultural Heritage Center (two volunteer staff), Tabernacle United Methodist Church, Noplace Baptist Church, Lighthouse Church of God |
|  | Partner Meeting (one every two months) | Mount Holypine Representative (leads), partner representatives attend |
| October – November 2018 | Advertisement for Spring 2019 graduate student assistants (for digitization) | Noplace Cultural Center volunteers and Mount Holypine College |
|  | Advertisement for Spring 2019 graduate student assistants (for online interface construction) | Noplace Cultural Center volunteers, Blair University |
|  | Advertisement for website/database developer that can train student interns and project manager | Noplace Cultural Center volunteers, Blair University |
|  | Partner Meeting (one every two months) | Mount Holypine Representative (leads), Partners |
| December 2018 | Continued development of finding aids | Mount Holypine College interns, Blair University |
|  | Interns for Spring 2019 are hired | Project Manager |
|  | The 20 weeks of the digitization (from mid-June to early December) produces 32,600 digitized pages | Mount Holypine College Interns |
| January 2019 | Training of 2 Mount Holypine graduate student assistants | Project Manager |
|  | Training of 2 Blair University website design assistants | Project Manager |
|  | Unpaid interns from Sinclair University start helping with the website: they post blogs, manage social media, etc. (continues in the months to come, as does digitization and website development) | Sinclair University interns |
|  | Outreach projects to notify public of the project’s progress | Noplace Cultural Heritage Center (two volunteer staff), Tabernacle United Methodist Church, Noplace Baptist Church, Lighthouse Church of God |
|  | Training of graduate student assistants with finding aid creation | Noplace Cultural Heritage Volunteers |
|  | Quality Control of Student Work | Project Manager |
|  | Metadata compiled | Blair University interns |
|  | Partner Meeting (one every two months) | Mount Holypine Representative (leads), Partners |
|  | All 34,720 diary pages are digitized! Mount Holypine College interns now focus primarily on finding aid creation. | Mount Holypine College Interns |
| February 2019 | A plan prioritizing which remaining digitized diaries appear online is developed | Project Manager, Mount Holypine College Interns, Blair University Interns, representatives from partner institutions |
|  | Assessment of digitization progress | Project Manager |
|  | User survey pertaining to website use satisfaction is created and distributed | Blair University interns |
|  | Classes at Mount Holypine begin transcribing diaries | Mount Holypine College |
| February-March 2019 | Digitized diary pages appear on the online database | Blair University interns |
|  | Finding aids appear on the online database | Blair University interns |
|  | Digitization continues | Mount Holypine College interns |
|  | Metadata compiled | Blair University interns |
|  | Classes at Sinclair University begin transcribing diaries (different diaries from those being transcribed by students at Mount Holypine) |  |
|  | Partner Meeting (one every two months) | Mount Holypine Representative (leads), Partners |
| April 2019 | End of project assessment | Project Manager, representatives from partner institutions |
|  | Write and submit final report to NEH | Project Manager |

- Budget Table

| CATEGORY | CATEGORY ITEMS/ SERVICES | AMOUNT | TOTAL $ |
| --- | --- | --- | --- |
| A. Salary/Benefits | Project Manager (Yearly Salary: $40,000) | $10,00 (25%) per year | $20,000 |
| B. Contractual Services | - 2 digitization interns from Mount Holypine College at $8.50 per hour per semester | One Intern: |  |
|  | Summer 2017 (6 weeks) | $1,020 | $2,040 |
|  | Autumn 2017 (14 weeks) | $2,380 | $4,760 |
|  | Spring 2018 (15 weeks) | $2,550 | $5,100 |
|  | Summer 2018 (8 weeks) | $1,360 | $2,720 |
|  | Autumn 2018 (14 weeks) | $2,380 | $4,760 |
|  | Spring 2019 (15 weeks) | $2,550 | $5,100 |
|  | - 2 website/ database interns from Blair University at $8.50 per hour per semester | One intern: |  |
|  | Spring 2018 (15 weeks) | $2,550 | $5,100 |
|  | Summer 2018 (8 weeks) | $1,360 | $2,720 |
|  | Autumn 2018 (14 weeks) | $2,380 | $4,760 |
|  | Spring 2019 (15 weeks) | $2,550 | $5,100 |
|  | - 2 transcribers transcribing the identified 40 volumes to be fully transcribed at $15.00 per hour | One transcriber |  |
|  | Summer 2017 (6 weeks) | $1,800 | $3,600 |
|  | Autumn 2017 (14 weeks) | $4,200 | $8,400 |
|  | - Preservationist (first 20 weeks, 20 hours per week) at $20.00 per hour | $8,000 | $8,000 |
|  | - Website/ Database Developer and Trainer (January 2018 – April 2018, 20 hours per week for 15 weeks) at $22.00 | $6,600 | $6,600 |
|  | - Mount Holypine College Representative leading Partner Meetings | $400 | $400 |
|  | - Volunteers at Noplace Cultural Heritage Center | $100 dollars per year | $400 |
|  | - Outreach administration at the three churches | $100 dollars per year per church | $600 |
|  | - Student Interns from Sinclair University | unpaid |  |
| C. Equipment | - 1 Fujitsu Scansnap Sv600 Contactless Scanner | - $ 1,088.16 | - $1,088.16 |
|  | - 25 archival boxes (10 diaries per box) | - 1 box= $10 | - $250.00 |
|  | - 1 5 Section Storage Cabinet/ Shelf | - 1,025.00 | - 1025.00 |
|  | - 40 (3 Packs Unbuffered Acid-free Paper for Storing and Preserving, 20 By 30 Inches 75 Sheets Total) | - $21.99 | - $879.60 |
|  | - 6 Hard-drive Storage | - $140 | - $840.00 |
|  | - 3 Computers | - $650 | - $1,950.00 |
|  | - Workstation | - $1,450 | - $1,450.00 |
| D. Library Materials | - Epson Expression 10000xl Scanner on loan from Sinclair University | $0 |  |
| E. Supplies/Postage/Printing | - Printing Advertisements for Worker Recruitment | $2.00 per page | $400.00 |
| F. Other Costs (specify) |  |  |  |
| TOTAL A through F |  |  | $98,042.76 |

- Budget Narrative

The overall budget comes out to approximately $98,042.76. While the Project Manager will perform everyday duties at Noplace Cultural Heritage Center, an additional 25% of his workday will be devoted to the project. 25% of his yearly earnings would be $10,000 per year. Because of the large reach of his duties and his interaction with interns, students, college faculty, the community, and churches, we feel as though this amount is justified.

Digitization interns from Mount Holypine College will work 5 hours per day, 4 days per week. They are critical for the digitization process. They will work for $8.50 per hour. Two digitization interns will work each semester. Having two digitization interns each semester will cost the following:

  - Summer 2017 (6 weeks of digitizing): $1,020

  - Autumn 2017 (14 weeks of digitizing): $2,380

  - Spring 2018 (15 weeks of digitizing): $2,550

  - Summer 2018 (8 weeks of digitizing): $1,360

  - Autumn 2018 (14 weeks of digitizing): $2,380

  - Spring 2019 (4 weeks of digitizing): $2,550

Two website/ database interns from Blair University will work at $8.50 per hour per semester starting in the Spring of 2018. Their involvement in the website greatly enhances access to the materials. Two website/ database interns will cost the following:

  - Spring 2018 (15 weeks of digitizing): $2,550

  - Summer 2018 (8 weeks of digitizing): $1,360

  - Autumn 2018 (14 weeks of digitizing): $2,380

  - Spring 2019 (4 weeks of digitizing): $2,550

The website/ database developer will greatly aid in the training of the first set of interns as all members of the project grow accustomed to the interface and understand its functions. The three additional computers will initially serve the two website/ database interns and the developer. However, once the developer leaves the project, the computer will be used by digitization interns or other staff working on finding aids.

Two transcribers will work for the first 20 weeks of the project transcribing the 40 diaries identified for full transcription. One diary (of pages varying from 100 – 200 in length) will be transcribed per week. Both transcribers will have roughly the same number of pages to transcribe. Because of the grueling task of the work, they will work 20 hour weeks and get paid $15.00 per hour.

Because so many of the diaries are in such poor condition, a preservationist is absolutely necessary. The preservationist will work the first 20 weeks at 20 hours per week, for $20.00 per hour. The preservationist will ensure that diary volumes can be digitized and help ensure the lasting nature of the materials. The archival boxes, cabinet, and acid-free sheets also help protect the diaries. Outreach programs initiated by the churches will involve the printing of flyers, scanning of their own supplemental documents, and hosting initiatives that promote community members to search through relevant materials in the family’s archives. The churches play a crucial marketing function to the project and need funding to reach constituents.

Lastly, the Fujitsu Scansnap Sv600 Contactless Scanner is needed because it safely scans the fragile diaries. Minimal manipulation of the pages/binding occurs with this type of scanner.